## Sheet1
Description | Assessment | Risk | Impact | Responsibility | Current Mitigation | Proposed Mitigation | Response | Tolerance
Database is attacked (e.g. SQL injection) and data is breached | Such attacks could expose sensitive information, such as passwords, which could have serious implications for users if they reuse their password on other sites. Such a breach could also have legal repercussions for Atos, so it is important to have measures in place to prevent this. At present the app does not store sensitive data, however later iterations of the app likely would. | Low | Medium | Atos development team | At present we do not use passwords, as our app does not yet have account functionality, and more generally our first sprint has focussed on basic functionality. As such, no measures have yet taken place, however the GCP database is encrypted. | In later iterations, back-end measures ot prevent attacks should be put in place, such as password hashing, as well as techniques such as parameterised variables. There could also be a requirement for a mimimum level of password complexity. | Bring the database offline and inform users via email that this information has been breached. Recommend that they change their passwords for other services that share breached password. | Treat
Malicious attempts made to overload the ticket queue (e.g. deliberately creating a large number of bogus tickets, thereby clogging up the ticketing system, and concealing genuine tickets) | Such attacks could overwhelm the IT support staff, and interrupt their normal workflow, which could cause serious interruptions for the company. | Low | Medium | Atos development team | None | Limits could be put in place, both in terms of the number of tickets that can be created in a given timeframe, as well as the number of tickets that can be generated from a given IP address within a certain timeframe. Alternatively, a security check could be made with each submission ('I am not a robot', for instance) | The start of the attack could be identified, and all tickets prior to the attack kept, and the rest removed. Alternatively, depending on the scale of the attack, personal judgement may have to be used to remove the likely bogus tickets manually. | Treat
If a system-wide issue occurs, the support staff may be innundated with ticket requests | Should an IT disruption occur that affects many staff, many genuine tickets may be issued at once, potentially overwhelming the ticketing team, and concealing tickets that may be urgent and unique to the other similar tickets | Medium | Medium | Atos development team | None | If a new, common issue is identified, IT support staff should be able to first prompt users to check if their issue falls within certain categories, and if so advising them that the issue is under investigation, thereby filtering out potentially unnecessary tickets | As per the proposed mitigation, the staff should keep an eye on the nature of the tickets, and create a prompt of this kind so that such issues can be mitigated | Tolerate
Database is deleted by attackers | As mentioned above, attackers can use SQL injections to drop tables and entire databases. | Low | Medium | Atos development team | As per row 1 | Regularly backup database on another machine to recall data in the case of data loss. | Switch to using backup SQL database while original is recreated as per the original setup. | Treat
HTTP traffic is monitored by an attacker | Connection between machines on the cloud network is currently insecure, meaning that information being sent via HTTP across the network can be easily monitored by individuals with malintent. Biggest risk is between the user and the web server as password information is sent unhashed and unencrypted. | High | High | Atos development team | None | Set up HTTPS connection across the network to encrypt information going to and from the system | If this occurs, it is unfortunately unlikely that we will be aware. If we are made aware, inform users via email that their information has been compromised and to change their passwords on other accounts should they use them elsewhere. | Treat
SQL database goes dark | If the SQL database service (provided by GCP) shuts down, the website will be rendered non-functional. | Low | Low | Google Cloud Platform | None | Set up a backup SQL database in the case of an outage | Bring website down. Attempt to spin the SQL database back up. Contact GCP for reasons why this occurred and possible mitigation in the future. | Tolerate
Web server goes dark | If the VM running the SpringBoot web server (provided by GCP) shuts down, the website will be rendered non-functional. | Low | Low | Google Cloud Platform | None | Set up a backup VM to spin up in the case of the first shutting down. | Attempt to spin the server up again. If this doesn't work, spin up a new VM and pull the installation files down from Git to run the server. Contact GCP for reasons why this occurred and possible mitigation in the future. | Tolerate